   Project Planning Phase
Milestone and Activity List
Date
21 October 2022
Team ID
PNT2022TMID14584
Project Name
        Customer Care Registry
TITLE
DESCRIPTION
DATE
Literature survey on the
28 SEPTEMBER 2022
Literature Survey &
selected project & gathering
Information Gathering
information by referring the,
technical papers,research
publications etc.
Prepare Empathy Map Canvas
Prepare Empathy Map
24 SEPTEMBER 2022
to capture the user Pains &
Gains, Prepare list of problem
statements
Ideation
List the by organizing the
25 SEPTEMBER 2022
brainstorming session and
prioritize the top 3 ideas
based on the feasibility &
importance.
Proposed Solution
Prepare the proposed solution
23 SEPTEMBER 2022
document, which includes the
novelty, feasibility of idea,
business model, social impact,
scalability of solution, etc.
Prepare problem - solution fit
30 SEPTEMBER 2022
Problem Solution Fit
document.
28 SEPTEMBER 2022
Prepare solution architecture
document.
Solution Architecture

---
Prepare the customer journey
Customer Journey
20 OCTOBER 2022
maps to understand the user
interactions & experiences
with the application (entry to
exit).
Prepare the functional
8 OCTOBER 2022
Functional Requirement
requirement document.
Data Flow Diagrams
Draw the data flow
9 OCTOBER 2022
diagrams and submit for
review.
Prepare the
10 OCTOBER 2022
Technology Architecture
technology
architecture diagram.
Prepare the milestones &
22 OCTOBER 2022
activity list of the project.
Prepare Milestone & Activity
List
Develop & submit the
IN PROGRESS..
Project Development -
developed code by testing it.
Delivery of Sprint-1, 2, 3 & 4